## Sheet1
Activity Name | Start Date | End Date | Doubts
Understanding the excel shared by Anish to create the data model | 2023-09-19 |  | How attendance is going to be captured in the system ? How monthly salary deductions should be captured in the system
Use Mongoose framework to create EmployeeSchema | 2023-09-19 |  | Clarification :Attendance data can be uploaded as an excel. It can also be manually entered.
EmployeeSchema work in progress | 2023-09-20 | 2023-09-24
EmployeeSchema coding | 2023-09-24 | 2023-09-24
Employee Model Save and validation | 2023-09-24 | 2023-09-24
Re write server side API using Model | 2023-09-25 | 2023-09-25
Re write schema loader using Model load some sample data | 2023-10-01
xlsx-style evaluation | 2023-10-02
read an excel stored in server | 2023-10-02 | 2023-10-02
parse the excel rows and columns | 2023-10-02 | 2023-10-02
load into mongoose | 2023-10-03 | 2023-10-07
throw validation errors and perform rollback | 2023-10-07 | 2023-10-08
date field import bug | 2023-10-08 | 2023-10-08 | in excel we have to store date columns as string and it will be of format dd-MMM-YYYY .. When displaying we have to convert it into locale string to get the original date
clean up program after insert | 2023-10-08 | 2023-10-08 | closed connection and log the import status
commit code | 2023-10-15 | 2023-10-15
integrate with List Employee screen | 2023-10-15 | 2023-10-15
use multi grid with fixed employee id column to display the data | 2023-10-15 | 2023-10-25
fix the styling issues | 2023-11-10 | 2023-11-10
testing the screen | 2023-11-18 | 2023-11-18
demo the screen
Create Employee Screen Client side
Create Employee Screen Servier side
Create Employee Screen Validations
Modify Employee
Navigation from List to Create screen
testing the screen
demo the screen
split the utility into a separate application

## Sheet2
Bugs
no error thrown but said import success | fixed