## Tasks
Activity Name | Start Date | End Date | Doubts
Understanding the excel shared by Anish to create the data model | 2023-09-19 |  | How attendance is going to be captured in the system ? How monthly salary deductions should be captured in the system
Use Mongoose framework to create EmployeeSchema | 2023-09-19 |  | Clarification :Attendance data can be uploaded as an excel. It can also be manually entered.
EmployeeSchema work in progress | 2023-09-20 | 2023-09-24
EmployeeSchema coding | 2023-09-24 | 2023-09-24
Employee Model Save and validation | 2023-09-24 | 2023-09-24
Re write server side API using Model | 2023-09-25 | 2023-09-25
Re write schema loader using Model load some sample data | 2023-10-01
xlsx-style evaluation | 2023-10-02
read an excel stored in server | 2023-10-02 | 2023-10-02
parse the excel rows and columns | 2023-10-02 | 2023-10-02
load into mongoose | 2023-10-03 | 2023-10-07
throw validation errors and perform rollback | 2023-10-07 | 2023-10-08
date field import bug | 2023-10-08 | 2023-10-08 | in excel we have to store date columns as string and it will be of format dd-MMM-YYYY .. When displaying we have to convert it into locale string to get the original date
clean up program after insert | 2023-10-08 | 2023-10-08 | closed connection and log the import status
commit code | 2023-10-15 | 2023-10-15
integrate with List Employee screen | 2023-10-15 | 2023-10-15
use multi grid with fixed employee id column to display the data | 2023-10-15 | 2023-10-25
fix the styling issues | 2023-11-10 | 2023-11-10
testing the screen | 2023-11-18 | 2023-11-18
demo the screen
Create Employee Screen Client side | 2023-12-16 | 2023-12-16
Create Employee Screen Servier side | 2023-12-16 | 2023-12-17 | open bugs = fixed
Create Employee Screen Validations | 2023-12-17 | 2023-12-17
Modify Employee | 2023-12-25 | 2023-12-26 | open bugs = fixed
Navigation from List to Create screen | 2023-12-27 | 2023-12-27
testing the screen | 2023-12-27 | 2023-12-27
demo the screen | 2023-12-27 | 2023-12-27
split the utility into a separate application | 2023-12-27 | 2023-12-27
Create Payroll | 2023-12-29 | 2023-12-29
Show payroll history | 2023-12-30 | 2023-12-30
No payroll exists message | 2023-12-30 | 2023-12-30
Invalid employee id message | 2023-12-30 | 2023-12-30
Save success message | 2023-12-30 | 2023-12-30
relisting after save | 2023-12-30 | 2023-12-30
implement clear | 2023-12-30 | 2023-12-30
Add company field to the employee master | 2023-12-31 | 2023-12-31
Add company column to the employee excel sheet | 2023-12-31 | 2023-12-31
Add company field to the create employee master screen | 2023-12-31 | 2023-12-31
Add company field in view employees screen | 2023-12-31 | 2023-12-31
Generate Salary screen
front end utility method to fetch no of days in a month | 2023-12-31 | 2023-12-31
front end utility method to calculate actual | 2023-12-31 | 2023-12-31
front end method to populate a formik field | 2023-12-31 | 2023-12-31
front end method to fetch the payroll data and store in a recoil state | 2023-01-01 | 2023-01-01
end to end | 2023-01-14 | 2023-01-14 | open bugs
Log Writing to File | 2023-01-14 | 2023-01-14
Salary Screen | 2023-01-14 | 2023-01-14
Disable auto complete | 2023-01-14 | 2023-01-14
Doubt : where is leaves availed used |  |  | clarification raised
Fix style issues | 2023-01-15 | 2023-01-15
Top Navigation Menu | 2023-01-15 | 2023-01-15
Changes to salary finalize
Generate Salary Screen Changes
Introduce "Save as Draft" -- Should be disabled if salary is finalized | 2023-01-16 | 2023-01-19 | open bugs = fixed
Introduce "Finalize" -- Should be disabled if salary is already finalized | 2023-01-16 | 2023-01-19
Visual enhancements to clearly show how salary is arrived | 2023-01-19 | 2023-01-19
Process Salary Screen Changes
Remove Finalize button from there | 2023-01-19 | 2023-01-19
Query all the finalized salary from DB | 2023-01-19 | 2023-01-19
No need to store information at a separate table | 2023-01-19 | 2023-01-19
No need of any validations at company level | 2023-01-19 | 2023-01-19
Export feature | 2024-01-26 | 2024-01-30
Make a new demo
Final Usability Enhancements
Navigation from Employee Details to Payroll and Salary Screen
Non Functional Requirements
Converting to a desktop app using enzyme
Encryption of sensitive data in .env files
Master Screen | 2024-01-25 | 2024-01-30
Add designation Master | 2024-01-25 | 2024-01-30
Add company Master | 2024-01-25 | 2024-01-30
PaySlip report automation | 2024-02-02 | 2024-02-02
Salary sheet report automation | 2024-02-02 | 2024-02-02
Salary acknowledgement report automation | 2024-02-02 | 2024-02-02
Folder location | 2024-01-30 | 2024-01-30
Cosmetic issues in report

## Bugs
Bugs
no error thrown but said import success | fixed
in save api the req.body is printing an empty obj | fixed
unable to see the date field as it is appearing blank | fixed by using .lean() function in Query API
once Alert Panel is dismissed not able to render new alerts | fixed
No message shown when payroll is not saved..instead shows a stack trac | fixed
Disable auto complete | fixed
Generate Salary Bugs
Clicked on clear employee code is not clearred | Fixed
Change the text "Enter the input fields to calculate salary" | Fixed
Premature button errors | Fixed
Salary is finalized still I am able to click on save… | Fixed
Date of Payment is not being checked | Fixed
Salary finalize message is not correct | Fixed

## Test data backup
A-300
Anish
9447757072
Anish Bhavan

## create employee screen
Sl.No
| Employee code | Employee Name
Contact Information | [6 empty] | Employment Information |  |  | Personal Information
| Address | Mobile Number |  |  |  |  | Designation | Date of joining | Status | Name of father / husband | Gender | Date of Birth | Marital Status
[7 empty] | Last Working Date | Date of Releaving | Remarks
Bank Information
| Bank Name | IFSC Code | Bank Account Number
Identity Information
| Pan Number | Aadhar Number | UAN EPF | EPF No | ESI Number | Welfare Fund Number
Nominees
| EPF Nominee | EPF Nominee Relation
| ESI Nominee | ESI Nominee Relation
| GPAIP Nominee | GPAIP Nominee Relation
| Gratuity Nominee | Gratuity Nominee Relation

## Generate Salary screen
Generate Salary screen
Input fields
EmployeeCode |  | Mandatory | should be a valid employee
Month | Number | Mandatory | should be a valid month
Year | Year | Mandatory | should be a valid year
List button
Days of attendance | Number | Mandatory | validation should be 0 < 31
Loss of pay days | Number | Mandatory | validation should be 0 < 31 | default =0
Number of weekly off granted | same as above |  |  | default =0
Overtime wages |  |  |  | default =0
Leave wages |  |  |  | default =0
National & Festival Holidays wages |  |  |  | default =0
Maternity Benefit |  |  |  | default =0
Advances |  |  |  | default =0
Welfare Fund |  |  |  | default =0
Professional Tax |  |  |  | default =0
Deduction of Fine |  |  |  | default =0
Deduction for Loss & Damages |  |  |  | default =0
Other Deduction |  |  |  | default =0
Calculate button | shows validate and populate values in the following table if there are no errrors
| Employee code | Employee name | Designation | Date of joining | Bank Name | IFSC Code | Bank Account Number | Days of attendance | Loss of pay days | Number of weekly off granted | Number of Leave granted | Basic | DA | Actual Basic | Actual DA | Gross Monthly Wages | HRA | city Compensation allowances | Other Allowances | Actual HRA | Actual City Compensation allowances | Overtime wages | Leave wages | National & Festival Holidays wages | Maternity Benefit | Actual Other Allowances | Risk Allowances | Total Amount | Employees Provident Fund | Employees State Insurance | Advances | Welfare Fund | Professional Tax | Deduction of Fine | Deduction for Loss & Damages | Other Deduction | Total Deduction | Net wages paid | Mode of Payment | Date of Payment
Source | employee master | employee master | employee master | employee master | employee master | employee master | employee master | user entry | user entry | user entry | user entry | payroll master | payroll master | formula | formula | formula | payroll master | payroll master | payroll master | formula | formula | user entry | user entry | user entry | user entry | formula | payroll master | formula | formula | formula | user entry | user entry | user entry | user entry | user entry | user entry | formula | formula | user entry | user entry
Save button | saves the data to salary master

## New Gen Salary Screen
Employee Details | Attendance Details | Salary BreakUp
Employee code | Days of attendance | Basic | Actual Basic | A
Employee name | Loss of pay days | DA | Actual DA | B
Designation | Number of weekly off granted | Gross Monthly Wages |  | A+B=C
Date of joining | Number of Leave granted | HRA | Actual HRA | D
Bank Name |  | city Compensation allowances | Actual City Compensation allowances | E
IFSC Code |  | Other Allowances | Actual Other Allowances | F
Bank Account Number |  | Overtime wages |  | G
|  | Leave wages |  | H
|  | National & Festival Holidays wages |  | I
|  | Maternity Benefit |  | J
Risk Allowances
|  | Total Amount |  | C+D+E+F+G+H+I+J
Deductions
|  | Employees Provident Fund |  | K
|  | Employees State Insurance |  | L
|  | Advances |  | M
|  | Welfare Fund |  | N
|  | Professional Tax |  | O
|  | Deduction of Fine |  | P
|  | Deduction for Loss & Damages |  | Q
|  | Other Deduction |  | R
|  | Total Deduction |  | K+L+M+N+O+P+Q+R
Net wages paid

## View Salary screen
View Salary Screen
Input fields
Month | Number
Year | Year
Company
Generate button | validates for the given month for all employees in that company have salary calculated
if valid generates the table in the below format